## AI - Project Completion
Project Progression
Milestone checklist |  |  |  |  | Achieved | Date | Milestones achieved
GitHub repository setup (group collaboration) |  |  |  |  | 1 | 2019-04-08 | 6
Incorporate A* search query technique |  |  |  |  | 1 | 2019-04-12 | Percentile of completion
Incorporate Depth-first search query technique |  |  |  |  | 1 | 2019-04-16 | 60%
Incorporate Breadth-first search (BFS) query technique (additional) |  |  |  |  | 1 | 2019-04-17 | Fractional completion
Testing implemented and thorough (improve upon errors) |  |  |  |  | 1 | 2019-04-18 | 0.6
Project program finalised by Team Members |  |  |  |  | 1 | 2019-04-19
Accompanying report finalised by Project Owner |  |  |  |  | 0
Presentation preparation complete (materials) |  |  |  |  | 0
Presentation complete (deliverable) |  |  |  |  | 0
All deliverables complete, and ready for submission |  |  |  |  | 0
Project Time Investment
Member of team |  |  | Week [1] |  | Week [2] |  | Week [3] | Totals
Member names |  |  | Time spent (hours) |  | Time spent (hours) |  | Time spent (hours) | Totalling time spent | Percentile of contribution
Adam Hubble |  |  | 30.75 |  | 40.5 |  | 0 | 71.25 | 39.28%
Josh Howitt |  |  | 0 |  | 0 |  | 0 | 0 | 0%
Alfie Horton |  |  | 30.15 |  | 25.25 |  | 0 | 55.4 | 30.54%
Joseph Hill |  |  | 27.25 |  | 27.5 |  | 0 | 54.75 | 30.18%
[7 empty] | Total time (group total) | 181.4 | 100%
[7 empty] | Total time (target total) | 200
Frequency Of Meetings (as a pair or group)
Day | Week [1] | Week [2] | Week [3] | Total number days met
1 | 1 | 1 | 0 | 10
2 | 1 | 1 | 0 | Attendance achieved
3 | 1 | 1 | 0 | 47.62%
4 | 1 | 1 | 0 | Fractional total
5 | 1 | 1 | 0 | 0.47619
6 | 0 | 0 | 0
7 | 0 | 0 | 0
ADAM HUBBLE ∙ JOSH HOWITT ∙ ALFIE HORTON ∙ JOSEPH HILL
Legend
--------------------------------------------------------------------------
Solid Colours (checklists)
Green Complete
Red Incomplete
--------------------------------------------------------------------------
Gradient Colours (completions)
Green Complete/ target met
Chartreuse Satisfactory/ target mostly met
Yellow Half complete/ target met midway
Amber Mostly incomplete/ target somewhat met
Red Incomplete/ target not met